## Read me
damantra — daily production planner
Template v1.0 · updated 2026-07-17 · damantra.app/resources/templates/daily-production-planner
HOW TO USE THIS PLANNER
1. Each morning, list the day's jobs on the Planner sheet with honest minute estimates.
2. Set the scheduled-capacity cell (B49) to the real production minutes available today — people × productive minutes, not contracted hours.
3. If total estimated minutes exceed capacity, decide what moves before the day starts.
4. Update the Status column as the day runs; plan tomorrow from what's outstanding.
5. Rows marked EXAMPLE are illustrative only — delete them before real use. The capacity value shipped in B49 is an editable example, not a recommendation.
NOTES
The totals block under the table is calculated and protected (no password — unprotect the sheet from the review menu if you need to restructure it).
The Planner sheet holds 40 job rows per day (rows 5–44) and the totals count only those rows. If a day needs more, start a second copy of the file or duplicate the sheet — do not insert rows below the totals block, they will not be counted.
Totals state arithmetic about your own estimates. This is a planning sheet, not scheduling software: it does not sequence machines, resolve conflicts, or update in real time.

## Planner
damantra — daily production planner
Template v1.0 · updated 2026-07-17 · damantra.app/resources/templates/daily-production-planner
Date | Job ref | Customer | Task | Process | Qty | Est. minutes | Priority | Operator | Machine | Start | Due | Status | Blocker / dependency | Notes
2026-07-17 | JOB-0041 | Example Customer Ltd | Press 45 transfers | DTF | 45 | 120 | High | A. Operator | Heat press 1 | 09:00 | 12:00 | Done |  | EXAMPLE — delete this row
2026-07-17 | JOB-0042 | Another Example Co | Embroider 12 polos | Embroidery | 12 | 45 | Standard | B. Operator | Emb head 1 | 13:00 | 16:00 | In progress | Awaiting thread delivery | EXAMPLE — delete this row
TOTALS (calculated — protected; capacity cell B49 is editable)
Total estimated minutes | 165
Total estimated hours | 2.75
Scheduled capacity (minutes) — editable | 420
Remaining capacity (minutes) | 255
Jobs completed | 1
Jobs outstanding | 1